Combined Sarawak Strategy and 
Affin Partners (consolidated)

Overview

Sarawak presents a strategic opportunity for Affin Bank to lead regional digitalisation by pairing FinTech partnerships with a Sarawak-first product and delivery approach. The state government’s digital agenda, large underbanked rural population, and SME-driven economy create a clear demand for tailored digital financial services.

Key constraints:

- Geography

- uneven digital infrastructure

- financial literacy and trust

- competitive activity that has not yet produced a dominant Sarawak-centric digital bank.

Strategic pillars (Affin + FinTech partnership focus)

- Financial Inclusion & Rural Onboarding: agent networks, BNPL/nano-credit at merchant points, simplified KYC and cash-in/cash-out workflows.

- Empowering SMEs & Agricultural Value Chains: supply-chain finance integrated with anchor corporate ledgers; bundled SME toolkits with payments and basic accounting.

- Seamless Everyday Payments: deep integration with state and super-app wallets, comprehensive biller coverage (SESCO, SWB, councils).

- Digital Lending & Wealth: alternative-data credit (P2P/co-lending), robo-advisory and low-cost investment access with localised education.

Implementation roadmap (phased)

- Phase 1 — Foundation & Pilot (0–12 months): MoU with Sarawak government, listening tours, pilots for agent banking (20 agents), supply-chain finance with one anchor, Affin link to S Pay Global, Sarawak Digital Hub in Kuching, staff training.

  - Early KPIs: MoU signed; 1,000 rural accounts via agents; 50 SMEs onboarded; 15% uptick in Affin-S Pay linkages.

- Phase 2 — Scale & Integrate (13–30 months): scale agents to 500+, expand supply-chain finance to 3–5 anchors, launch Affin Sarawak SME Digital Toolkit, P2P Sarawak SME Fund, micro-insurance; integrate with state service payments and tourism wallet guides.

  - Scale KPIs: 50,000 new rural accounts; 500+ SMEs active; 5,000 SME Toolkit sign-ups; MYR 20M loans disbursed; Affin top bank for state payments.

- Phase 3 — Innovate & Lead (31–48+ months): green finance, blockchain provenance pilots, annual FinTech challenge, Affin Digital Sarawak report, profitability and cost-to-serve optimisation.

- Long-term KPIs: MYR 5M green loans; blockchain pilot live; 50+ startup applicants; digital channel profitability > branch.

Governance & success factors

- Dedicated cross-functional Sarawak team with decision authority.

- Agile test-and-learn culture; rapid iteration on pilots.

- Data-driven KPIs for adoption, transactions and revenue.

- Ongoing regulatory engagement with BNM and state agencies.

- Localised brand messaging: “Banking for Sarawak’s Future.”

Operational design considerations

- Low-bandwidth API design, sandbox SFTP/testing environments, templated onboarding docs (board resolutions, authorisations), token provisioning SOPs.

- SIT → UAT → PVT → production release controls with regression testing and GL reconciliation test cases.

- Agent onboarding playbooks, agent liquidity and settlement flows, dispute handling and incident SLAs.

- Training materials and local language content for financial literacy and product adoption.

Known & relevant Affin partners (cash management / merchant / fintech / tech)

- ACI Worldwide — payments platform to modernise and centralise real-time payments.

- Aspire Systems — digital banking / omnichannel implementation partner.

- F5 — digital operations / agility technology partner.

- Versa Asia / AFFINMAX — digital cash-management/mobile savings and SME ecosystem solutions.

- Merchantrade (Merchantrade Money) — co-branded prepaid card and e-wallet integration.

- Fiuu — merchant ecosystem partnership for merchant recruitment and SME cashless payments.

- PayNet / FPX — transaction rails and online collections capability.

- DuitNow / DuitNow AutoDebit — recurring collection/payment rails.

- Halogen Capital — distribution partnership for digital asset/Shariah defensive bitcoin product.

- AFFIN Group / SME Colony references — platforms and SME references supporting SME digitalisation.

Notes: these partners cover enterprise payments, merchant acquiring, SME platforms, wallet/co-branding, and fintech distribution roles. Additional partners and vendor details are discoverable via Affin newsroom, annual reports, Malaysian fintech press and vendor partner pages.

How to find more partners (practical steps)

- Check Affin Group / Affin Bank newsroom and press releases for announced partnerships.

- Review Affin Group annual reports and investor presentations for vendor disclosures.

- Search Malaysian fintech and business press for merchant acquiring and cash-management stories.

- Inspect partner/vendor websites (payment processors, core vendors, card schemes) for client lists naming Affin.

Appendix — one-page achievement highlights for Jay

- CMS migration: led full customer migration to new CMS; completed before 31 Dec 2018; minimal downtime; coordinated UAT/PVT and cross-functional teams.

- Reflex platform: managed channel and ops; reduced incident resolution times; increased subscribers via product and marketing campaigns.

- API merchant integration: oversaw end-to-end API implementation, sandbox/SFTP setup and GL reconciliation test cases leading to successful merchant onboarding.

- Team leadership: built and coached cross-functional teams in Transaction Banking and Sales achieving activation and current-account uplift targets.